## BOM Scoping
Activity No. | Driver Description | UOM | Inclusions | Exclusions
1 | Download Documentation | Site | • Pull the following documents from the database of record: Drone Survey, RFDS, CDs, and MA/SA | • Order drone survey • Build SP assignment • Pull documents from IWM
2 | SoW Summary | Site | • Summarize SoW using the scoping template • Load to ESR Site Engineering Notes/United Script | • Troubleshooting tool errors
3 | Create BOM | Site | • Create REV 1 Bill of Material (BOM) • Upload to Ericsson tool • Validate Preliminary REV 0 BOM | • Preliminary REV 0 BOM creation
4 | SoW & BOM Submission | Site | • Submit REV 1 SoW • Submit BOM to CX SP for review | • Troubleshooting tool errors
5 | CX SP Handshake | Site | • Coordinate and complete meetings with CX SPs • Agree on BOM for SoW | • Cost negotiations
6 | Tool of Record Update | Site | • Update the BOM status and other milestones • Update Scoping Complete Forecast and Actual • Add notes in the database | • Milestones unrelated to scoping
7 | BOM Approval | Site | • Complete final BOM approval activity in the tool of record
8 | Scoping Meetings | Site | • Attend Scoping Team meetings | • Attend customer meetings
9 | Performance & Governance | Site | Supplier Lead CM/PM responsibilities: • Attend local market meetings • Respond to market questions and concerns by email • Address technical questions • Provide status updates • Perform quality reviews • Track site-scoping progress

## Site Design Scoping
Activity No. | Driver Description | UOM | Inclusions | Exclusions
1 | Download Documentation | Site | • Pull the following documents from tool of record: Preliminary RFDS and historical documents (CDs, MA, and SA) • Request historical documents from the E// GND group for upload to Site Tracker | • Order drone survey • Pull documents from customer's system
2 | SoW Summary | Site | • Populate required document for site design scoping • Redline customer documents (PCDs, MA, and SA) • Attend customer meetings • Ensure completed SoW packages meet Customer's Build Standards | • Troubleshooting tool errors
3 | SoW Submission | Site | • Submit SSDs in tool of record • Submit SSDs in E// SharePoint | • Troubleshooting tool errors
4 | Tool of Record Update | Site | • Update the BOM status and other milestones • Update Scoping Complete Forecast and Actual • Add notes in the database | • Milestones unrelated to scoping
5 | Redlining | Site | • Redline CDs, RFDS, MA, and SA to better define the SoW • Document issues and discrepancies • Return documents to A&E when applicable | • RFDS promotion or demotion
6 | Scoping Meetings | Site | • Attend Scoping Team meetings • Attend Customer SAQ Scoping meetings and present design to the customer • Address issues and recommend solutions related to onsite conditions, material conflicts, and overall SoW efficiency
7 | Performance & Governance | Site | Supplier Lead CM/PM responsibilities: • Attend local market meetings • Respond to market and customer questions and concerns • Address technical questions • Provide status updates • Perform quality reviews • Track site-scoping progress

## Network Deployment Scoping
Activity No. | Driver Description | UOM | Inclusions | Exclusions
1 | Download Documentation | Site | Pull Pre-NTP documents from database (Final RFDS, Final CD, SA, MA, BOM); retrieve historical documents (CDs, MA, SA) | Order drone survey; pull documents from customer's system
2 | Documentation Review & Validation | Site | • Review available site-specific documentation to understand the proposed construction scope. • Identify the current/existing site configuration and proposed configuration. • Identify new, existing, relocated, reused and removed equipment, as applicable. • Cross-check applicable design documents for consistency. • Identify discrepancies, conflicting information or missing information affecting the scoping activities. • Identify items requiring clarification and prepare applicable RFIs for Ericsson review. • Determine the latest/applicable documentation to be used for scoping based on available document revisions and project information. | • Engineering/design changes. • Resolution or approval of engineering/design discrepancies. • Customer approval of RFIs or proposed design changes. • Structural engineering analysis or design.
3 | Add FPP Service Drivers | Site | • Develop the Scope of Work based on the applicable site documentation. • Identify equipment to be installed, removed, relocated or reused, as applicable. • Add Services Drivers | • RF engineering or design changes. • Selection or substitution of RF equipment not defined by the approved design documentation. • Assumption of cable/trunk lengths when not supported by project documentation or applicable scoping rules. • Resolution or approval of design discrepancies.
4 | Requirements Identification & DPP | Site | * Identify if Crane/Man-lift is required * Identify rigging requirements and update * Identify any 3rd party services that are required * Identify safety/Risk issues and report to E/// EH&S Managers
5 | SP Quote Negotiation | Site | * Coordinate and complete SOW/BOM Desktop Review meetings with CX SPs * Agree on SOW, BOM, Service Drivers, Crane, etc. * Submit updated SOW and BOM with Matrix Drivers to SP | * Troubleshooting tool errors
6 | Database of Record Update | Site | * Update the Services Package status and other milestones * Scoping complete Forecast & Actual * Add notes in database | * Milestones non-Scoping Related
7 | Time Estimate | Site | * Calculate CX cycle time estimate and update to Ericsson * Complete & upload the calculator template
8 | Scoping Meetings | Site | * Attend Scoping Team meetings (Cx meetings with CMs and SPs) | * Attend customer meeting * Attend CU Meetings
9 | Quote Submission | Site | * Process quote in database of record
10 | Performance & Governance | Site | • Supplier Lead CM/PM to attend applicable Ericsson scoping meetings. • Respond to Ericsson questions and concerns. • Address technical questions related to performed scoping activities. • Provide status updates. • Perform quality review of completed scoping packages. • Track site scoping progress and open actions. • Support Ericsson Scoping Lead with issue identification and escalation. | • Direct customer representation/decision-making unless specifically authorized. • Activities outside the defined Rogers scoping scope. • Final engineering, commercial or customer approvals.